## Setting up AWS Env
Sr. No. | Tools and Service | Scope of Work Details |  | Questions
1 | Architecture Design and Implementation | Design a private network architecture with subnets, route tables, and security groups. | Design a private network architecture to ensure security and isolation of application components. Implement subnets, route tables, and security groups as per AWS best practices. | 1. Is it correct to assume that all application stacks should be on a private network?
|  | Implement a Bastion host with WAF for secure access. | Setup a Bastion host (EC2 instance) as a gateway for secure SSH access into the private network. Configure AWS WAF (Web Application Firewall) to protect against common web exploits and ensure secure access to the Bastion host. | 2. Please share the development platform details for all three stacks (Frontend/Web tier, Application tier, and Backend/Database tier).
|  | Setup Load Balancer (ALB/NLB) for high availability and scalability. | Implement an Application Load Balancer (ALB) or Network Load Balancer (NLB) to distribute incoming application traffic across multiple targets (EC2 instances). Configure health checks and ensure high availability. | 3. Is it mandatory to keep the frontend and backend DB on Docker containers? If not, a. Can we host the frontend on an S3 bucket and serve it via CloudFront? b. Can we use Amazon RDS for the database?
2 | Containerized Application Deployment | Containerize frontend (ReactJS) and backend (multilingual platform) applications using Docker. |  | 4. Can we use Amazon ECR to store the Docker images instead of an EC2 instance?
|  | Utilize Docker Compose or similar for multi-container application management. |  | 5. Do we need High-Availability (HA)?
|  | Configure CI/CD pipeline for automated builds and deployments. |  | 6. Do we need Docker orchestration services? If yes, which tool do you prefer (e.g., Kubernetes, Portainer)?
3 | Database Setup and Management | Containerize database (e.g., PostgreSQL, MySQL) using Docker. | Containerize the database using Docker for flexibility and consistency in deployment. Deploy and manage the database (e.g., PostgreSQL, MySQL) using Docker volumes for data persistence. | 7. What are the database size and performance requirements?
|  | Connect backend application to Amazon RDS for managed database service. | Connect the backend application to Amazon RDS for a managed database service. Configure RDS instances with appropriate instance types, storage, and backup settings. | 8. How frequently should automated backups be taken for RDS?
|  | Implement backup strategy using RDS automated snapshots. | Implement automated backups using RDS automated snapshots for data protection. Setup a Disaster Recovery (DR) instance with synchronized data for failover scenarios. Ensure block-level snapshots are configured and maintained for both production and DR instances. | 9. How will data replication be managed between production and DR instances?
4 | Security and Access Control | Establish SSL encrypted links between backend application and RDS. |  | 10. What are the specific security requirements or compliance standards (e.g., GDPR, HIPAA) that need to be followed?
|  | Configure VPN access for highly privileged users to RDS. |  | 11. How will access control and user authentication be managed within AWS IAM (Identity and Access Management)?
Secure Bastion host access via VPN and IP whitelisting.
Enable port knocking for additional Bastion host security.
5 | Networking and Infrastructure | Whitelist outgoing API calls via DNS or relevant mechanisms. |  | 12. What are the external API integrations that require whitelisting for outgoing communication?
|  | Utilize AWS SES for outgoing emails from the application. |  | 13. Are there specific networking requirements for integrating with external services or partners?
6 | Deployment and Orchestration | Setup CI/CD pipeline for automated Docker image builds and deployments. |  | 14. What is the expected deployment frequency (e.g., weekly releases)?
|  | Use self-hosted Docker orchestration tool (e.g., Portainer). |  | 15. Do you have existing CI/CD pipelines or deployment tools that need integration with the AWS environment?
Integrate with version control systems for automated deployments.
7 | Performance and Scalability | Specify server configurations (vCPU, RAM, SSD) for optimal application performance. |  | 16. What are the expected peak loads and concurrent user sessions that the infrastructure needs to support?
|  | Provision attachable volumes as required for data storage. |  | 17. Are there seasonal or periodic traffic variations that need to be accommodated in the scalability plan?
8 | Environment and Configuration Management | Setup Production environment with plans for future environments (DEV/UAT). |  | 18. What are the requirements for environment isolation and configuration management (e.g., separate AWS accounts or VPCs)?
|  | Maintain infrastructure as code (IaC) using AWS CloudFormation or Terraform. |  | 19. Are there specific compliance or governance policies that need to be implemented for environment configuration?
|  | Document configuration scripts and ongoing maintenance procedures. |  | 20. How should monitoring and logging be configured to ensure compliance and operational visibility?
Timeframe (Days)
1 | Planning and Design | 2
2 | Setting Up Networking and Security | 1
3 | Containerized Application Deployment | 1
4 | Database Setup and Management | 1
5 | Security and Access Management | 1
6 | Deployment and Monitoring | 2
7 | Environment Configuration | 2
8 | Testing and Validation | 1
Total |  | 11

## Scope of Work - DevOps
Sr. No. | Task / Activity | Description | Questions to Client
1 | Planning and Design
| Review Requirements | Thoroughly analyze client requirements, compliance needs, and preferences. | What are your primary objectives for this AWS environment setup?
| Architectural Design | Design AWS VPC architecture, subnet layout, and network security model. | Are there any specific compliance requirements we need to adhere to?
| High Availability (HA) Considerations | Plan for multi-AZ deployments and fault tolerance. | What are your preferences regarding AWS region for hosting the environment?
2 | Infrastructure Setup
| VPC and Networking Setup | Create VPC, subnets, internet gateways, NAT gateways as per design. | Could you provide a high-level overview of your desired VPC architecture?
| Security Groups and ACLs | Configure security groups and network ACLs for traffic control. | How many availability zones should we utilize for redundancy?
| Bastion Host and WAF Setup | Deploy Bastion host and integrate with AWS WAF for web app security. | How do you envision integrating your existing WAF and gateway with AWS?
3 | Application Deployment and Containerization
| Containerized Applications | Dockerize frontend and backend applications as required. | What are the development platform details for your frontend and backend?
| Container Orchestration | Choose Docker orchestration tool (e.g., Kubernetes, Portainer). | Do we need to containerize both frontend and backend applications?
| CI/CD Pipeline | Set up CI/CD pipeline for automated builds and deployments. | If not, what alternatives do you prefer?
4 | Database Management
| Amazon RDS Setup | Provision RDS instances for relational databases (e.g., MySQL, PostgreSQL). | What database technologies and configurations do you prefer for production?
| Data Security | Implement SSL encryption and IAM roles for database access control. | How do you plan to integrate external APIs and services with the database?
5 | Monitoring and Logging
| CloudWatch Integration | Configure CloudWatch alarms and monitoring for EC2, RDS, and applications. | What are the specific metrics or monitoring requirements for your applications?
| Logging and Auditing | Set up logging for application and infrastructure events. | Do you have any preferences for logging tools or services?
6 | Security and Access Management
| IAM Role Management | Define IAM roles, policies, and permissions for users and applications. | How will administrative access to the environment be managed?
| Security Best Practices | Implement encryption, access control, and adhere to AWS security best practices. | Are there any specific security measures or configurations we should implement?
7 | Backup and Disaster Recovery
| Backup Strategies | Design backup procedures for EC2 instances, RDS databases, and data. | What are your requirements for backup frequency and retention?
| Disaster Recovery (DR) Planning | Plan for DR scenarios and automated failover mechanisms. | How critical is disaster recovery planning for your environment?
8 | Documentation |  | Do you require detailed documentation of the AWS environment setup?
9 | Optimization and Scalability
| Cost Optimization | Monitor AWS usage and optimize costs through efficient resource utilization. | Are there any specific budget constraints or cost optimization goals?
| Scalability Planning | Plan for auto-scaling and capacity management based on workload demands. | How do you envision scaling your application in the future?

## Flow
Sr. No. | Task | Flow
1 | Architecture Design and Implementation | - Design a private network architecture.
- Implement a Bastion host with WAF for secure access.
- Setup Load Balancer (potentially using EC2 instances) for high availability and scalability.
2 | Containerized Application Deployment | - Containerize the web server using an open-source container host.
- Utilize Docker for frontend (ReactJS) and backend (multilingual platform).
- Ensure containers are deployed securely and efficiently.
3 | Database Setup and Management | - Containerize the database using Docker.
- Connect to Amazon RDS for production database.
- Implement backup strategy using RDS automated snapshots.
4 | Disaster Recovery Setup | - Configure DR instance with backup database and snapshot storage.
- Implement block-level snapshots for both production and DR instances.
5 | Security and Access Control | - Establish SSL encrypted links between backend application and RDS.
- Configure VPN access for highly privileged users to RDS.
- Secure Bastion host access via VPN and IP whitelisting.
6 | Networking and Infrastructure | - Whitelist outgoing API calls via DNS or relevant mechanisms.
- Setup AWS SES for outgoing emails.
7 | Deployment and Orchestration | - Implement CI/CD pipeline for Docker image builds.
- Use a self-hosted Docker orchestration solution (e.g., Portainer).
- Ensure deployment procedures are efficient and scalable.
8 | Performance and Scalability | - Design infrastructure to handle 5000 requests per second.
- Specify server configurations (4 core, 8 GB RAM, 50 GB SSD) for optimal performance.
9 | Environment and Configuration Management | - Setup single Production environment with plans for future environments.
- Maintain infrastructure as code (IaC) for configuration management.