## POA
| Activity Name | Details
| Client ID and Customer Name | Client : NCRTC (7141)
Project Name
| Requested Activity Name | OCP Test Cluster Upgrade
Ticket ID
| Activity Requisition By | Customer/PM/SD/Co-ordinator
Date of Requisition
| Number of Linux servers in Activity | 14
Scheduled Date of the Activity
Start Time of the Activity
End Time of the Activity
| Maintenance Window | 24 Hours
| Server Downtime Window | 24 Hours
Owner/Responsibility
| Approval for Activity | 1) Customer / App-DB Vendor to provide approval on Ticket for OCP Upgrade | Customer / App-DB Vendor
|  | 2) Customer / App-DB Vendor to provide approval on Ticket for restart application/services or reboot OCP cluster, If required, to reflect changes on OCP cluster. | Customer / App-DB Vendor
Sr.No. |  |  | Owner/Responsibility
1 | Activity Requirement and Pre-activity Task | 1) Check the health of the existing OpenShift cluster using the oc command and resolve any existing issues. | DevOps Team
|  | 2) Ensure that the infrastructure and nodes meet the resource requirements of the target OpenShift version.Ensure that the infrastructure and nodes meet the resource requirements of the target OpenShift version. | DevOps Team
|  | 3) upgrade any installed operators (like the Cluster Version Operator) to versions compatible with the target OpenShift release. - If required | DevOps Team
|  | 4) Validate the health of individual nodes in the cluster. Investigate and resolve any node-related issues. | DevOps Team
|  | 5) Verify the health of storage solutions such as Persistent Volumes (PVs) and Persistent Volume Claims (PVCs). Resolve any pv, pvc-realated issues. | DevOps Team
|  | 6) Thoroughly review the release notes of the target OpenShift version to understand new features, changes, and any known issues. | DevOps Team
|  | 7) Verify that all installed applications, add-ons, and plugins are compatible with the target OpenShift version. | DevOps Team
|  | 8) Ensure a complete backup of critical data, configurations, and persistent volumes before initiating the upgrade. | DevOps Team
|  | 9) Develop a communication plan to inform all stakeholders about the upgrade schedule, potential downtime, and any impact on services. | DevOps Team
|  | 10) Define a rollback plan in case the upgrade encounters issues. Document the steps and criteria for deciding when to initiate a rollback. | Techsetup Team
|  | Note : a) Backup or clone will be taken 5-6 hours before the schedule activity. | Backup Team
Owner/Responsibility
2 | Important notes for OCP cluster updating Activity | 1)Monitor Progress Continuously: Keep a constant check on the upgrade progress. Utilize monitoring tools to track the status of individual components and nodes throughout the upgrade process. | DevOps Team
|  | 2) Follow Upgrade Steps Carefully: Adhere strictly to the documented upgrade steps provided by OpenShift. Skipping steps or deviating from the recommended process can lead to unforeseen complications. | DevOps Team
|  | 3) Verify Component Readiness: Ensure that each component—control plane nodes, worker nodes, networking, storage, and add-ons—successfully completes the upgrade process before moving to the next step | DevOps Team
Owner/Responsibility
3 | Any suggession by Client for the Activity | While attempting to upgrade a cluster from version 4.10.55 to 4.12.45 an error occurred. The error message states that the Cluster operator "operator-lifecycle-manager" should not be upgraded between minor versions due to an issue with incompatible operators. Specifically, the ClusterServiceVersion "amq-streams/amqstreams.v1.8.4" is identified as incompatible with OpenShift minor versions greater than 4.9. The challenge lies in the fact that the operator is associated with an IBM application, and modifications cannot be made to it. Assistance is sought from the client to address this issue. | Client/Application Team
Owner/Responsibility
4 | Activity Steps | 1) Enable maintanance mode in Monitoring for Linux servers on Prod | Monitoring Team
|  | 2) Prod Master resource increase if required | DevOps Team
|  | 3) Cluster Upgaradation(We will increase resource size for temprary purpose only) - 4.12.45 | DevOps Team
|  | 4) Reboot Server multiple times during OCP upgrade activity as per requirement. | Customer / App-DB Vendor
|  | 5) Increase Ring Buffer size | DevOps Team
|  | 6) Enable Garbage collection | DevOps Team
|  | 7) Changes in Mutating webhook | DevOps Team
|  | 8) Confirm that Linux server is online again along with mountpoints and IP routes | DevOps Team
|  | 9) Remove maintainance mode in Monitoring for Linux server | Monitoring Team
Owner/Responsibility
5 | Post Activity Check and Confirmation | 1) Customer / App-DB Vendor Team will start required application/services | Customer / App-DB Vendor
|  | 2) Customer / App-DB Vendor Team will confirm us on Ticket about successful completion of the activity. | Customer / App-DB Vendor
Owner/Responsibility
6 | Roll Back Plan | 1) During the activity, if there is any issue with OCP, then Backup Team will restore the VM using latest available backups. | Backup Team
|  | 2) If Customer / App-DB Vendor report any issue with OCP after the activity, then Backup Team will restore the VM using latest available backups. | Backup Team
|  | 3) Customer / App-DB Vendor Team will confirm us on Ticket about application/services running fine on the restored OCP Cluster. | Customer / App-DB Vendor
|  | 4) Customer / App-DB Vendor Team will confirm us on Ticket for deleting original OCP Server. | Customer / App-DB Vendor
|  | 5) Original OCP cluster VM / server will be deleted from the backup after 48 hours from the date of activity. | Techsetup Team
|  | 7) Billing record will be upgraded for the restored OCP cluster server details with the help of Billing Team if both old and newly restored VMs are required. | PM/SD
Owner/Responsibility
7 | Contact Person details during the Activity | 1) DevOps Team | DevOps Team
|  | 2) PM / SD / Project Co-ordinator | PMO Team
|  | 3) Linux Team | Linux Team
4) Client / Application Team
|  | 5) CRM | CRM Team
Owner/Responsibility
8 | Important Note for Activity | 1) If there is any dependancy on Customer/Application/DB Team for the requested changes on OCP server, then Customer/Application/DB Team will stop/start/restart necessary application/services/cluster/replication etc. on OCP server and upgrade DevOps Team on the ticket. | Customer / App-DB Vendor
|  | 2) DevOps Team will upgrade Ticket as and when required from the time when POA is shared to till the time of completion of the activity. | DevOps Team
|  | 3) PM/SD/CRM/Co-ordinator will communicate with client as and when required from the time when POA is shared to till the time of completion of the activity. | PM/SD/CRM/Co-ordinator
|  | 4) PM/SD/CRM/Co-ordinator will communicate with Other ESDS Teams as and when required from the time when POA is shared to till the time of completion of the activity. | PM/SD/CRM/Co-ordinator
|  | 5) If activity is cancelled/postponed by customer, then create new Ticket for scheduling acivity with new date. Also confirm if fresh backups needs to be triggered. | Customer / PM
|  | 6) If the scheduled activity is not done/failed or postponed due to any unavoidable situation, then create new Ticket for scheduling acivity for pending servers with new dates as per next available activity slot. | Customer / PM
|  | 7) Delete any onetime backup / clone VM after 48 hours from the date of successful completion of the activity. | Backup/Techsetup Team

## Pre Upgradation
Activity Name | Details | Owner/Responsibility
1.Critical Importance of Resource Upgradation: | It cannot be overstated that upgrading the resources of our cluster is of paramount importance, a point that has been reiterated multiple times and validated by IBM. Failing to address this crucial aspect during the upgrade process of the OCP cluster poses a significant risk of halting the entire operation due to inadequate resources. Insufficient resources could impede the seamless execution of tasks and compromise the overall efficiency of the cluster. | Customer
2.Encountered Challenge During Dev Environment Upgrade: | Our recent attempt to upgrade the Dev Environment brought forth a noteworthy challenge. This challenge materialized when our worker nodes encountered degradation issues stemming from complications with the Machine Config Pool. As a result, during the execution of the upgrade process, the cluster itself initiated node drain process. However, an unforeseen issue arose as the application pods associated with daemon sets failed to be properly evicted, leading to the entrapment of nodes within the cluster. | Customer
| To proactively address and prevent similar obstacles in upgrade endeavors, it is strongly advised to take preemptive measures such as the complete removal or suspension of application pods before commencing the upgrade activity. These pods can then be re-deployed post-upgrade, ensuring a smoother transition and mitigating the risks associated with node stagnation. Adherence to this recommended protocol would not only enhance the efficiency and reliability of upgrade operations but also significantly reduce the likelihood of node entrapment, thereby ensuring uninterrupted cluster functionality. | Customer
Given the fulfillment of these conditions, we anticipate that cluster upgrades can be accomplished within a timeframe of 24 hours.

## Linux Servers
Sr.No. | Server Private IP Address | VM Name | Server Login Details in secure link | Linux OS Version | OCP version Before updates | Enviornment [ DEV/TEST/PROD ] | Server Usage [ Haproxy LB / PCS Cluster / CRM Cluster / Oracle RAC ] | Impotant Note for the server | Backup Details | OCP update Status [Completed / Not-Completed] | OCP Version After OCP update
1 | 10.48.132.2 | ESDS-7141-45350-Prd1 |  | RHEL 4.10 (Ootpa) | 4.10.55 | Prod | No
2 | 10.48.132.3 | ESDS-7141-45349-Prd2 |  | RHEL 4.10 (Ootpa) | 4.10.55 | Prod | No
3 | 10.48.132.4 | ESDS-7141-45348-Prd3 |  | RHEL 4.10 (Ootpa) | 4.10.55 | Prod | No
4 | 10.48.132.7 | ESDS-7141-45347-workerprd1 |  | RHEL 8.7 (Ootpa) | 4.10.55 | Prod | No
5 | 10.48.132.8 | ESDS-7141-45346-workerprd2 |  | RHEL 8.7 (Ootpa) | 4.10.55 | Prod | No
6 | 10.48.132.9 | ESDS-7141-45345-workerprd3 |  | RHEL 8.7 (Ootpa) | 4.10.55 | Prod | No
7 | 10.48.132.10 | ESDS-7141-45344-workerprd4 |  | RHEL 8.7 (Ootpa) | 4.10.55 | Prod | No
8 | 10.48.132.11 | ESDS-7141-45343-workerprd5 |  | RHEL 8.7 (Ootpa) | 4.10.55 | Prod | No
9 | 10.48.132.12 | ESDS-7141-56311-workerprd6 |  | RHEL 8.4 (Ootpa) | 4.10.55 | Prod | No
10 | 10.48.132.13 | ESDS-7141-56310-workerprd7 |  | RHEL 8.4 (Ootpa) | 4.10.55 | Prod | No
11 | 10.48.132.14 | ESDS-7141-56309-workerprd-8 |  | RHEL 8.4 (Ootpa) | 4.10.55 | Prod | No
12 | 10.48.132.15 | ESDS-7141-56308-workerprd9 |  | RHEL 8.4 (Ootpa) | 4.10.55 | Prod | No
13 | 10.48.132.16 | ESDS-7141-56307-workerprd10 |  | RHEL 8.4 (Ootpa) | 4.10.55 | Prod | No
14 | 10.48.132.17 | ESDS-7141-56306-workerprd11 |  | RHEL 8.4 (Ootpa) | 4.10.55 | Prod | No